## Slide 1: Process Safety Deliverables for Projects
December 6, 2023
Tim Hoff
EMTEC Process Safety Engineering - Projects SME

## Slide 2: Tim Hoff Bio
ExxonMobil Process Safety SME for Global Projects
B.S. in ChemE from Purdue University (2001)
Variety of roles within EM
  Project Development, Process Design, and Execution/Start-up
  Senior Operations Engineer for Alkylation and Light Ends Fractionation
  Site Process Safety Engineer
  Technical Process Safety Lead for Northeastern Operating Sites

## Slide 3: Why Do We Even Do Projects?
Projects are critical to enable continued safe and profitable operations
  Meet new or updated regulations
  Reduce residual risk
  Maintain facilities to retain profitability
  Build for new ventures/opportunities
Projects vary greatly in cost and scope and hazards
  Installation of a new fume hood in a lab (6 months)
  Development and construction of a $4B chemical production facility (5-7 years)
External pressures abound to complete projects in the most cost-effective and efficient means available

## Slide 4: General Project Management System

## Slide 5: 2022 ExxonMobil Project Arrow – Gates & Check Points
Objectives of Gates and Check Points
Gate 1 – Determine where a business opportunity or need should be pursued and alternatives developed in Stage 2
Gate 2 – Decide if optimum concept has been selected and delineated from a business and project management perspective (“go / no-go” decision)
CP1 – Confirm that the optimization of the scope of the project has been completed and that FEED is ready to be commenced
Gate 3 – Support readiness for Appropriation and advancement to Execution. Decide if the project is acceptable from a business and project management perspective.
CP2 – Confirm that the construction of the project is ready to be commenced
CP3 – Confirm that the project is ready to proceed to Startup and turnover to Operations

## Slide 6: Late Scope Change Can Be Painful
Hazards or major risks identified later in a project’s life cycle can be costly to mitigate
Late scope change can lead to major execution delays or redesign of equipment in production stage
When is the right time to complete process safety reviews?
  Too early, not enough definition
  Too late, major cost/execution concerns

## Slide 7: Process Safety Deliverables – Selection Stage
Assignment of process safety engineer to project teams
Development of risk management plan
  Outlines processes and studies to identify, analyze, manage, and accept discovered risk in a project
Key Selection Stage Process Safety Reviews:
  HAZID/ISHER/SHE Review
  Preliminary Safety Relief Reviews
  Early Facility Layout and Building Siting Reviews

## Slide 8: Process Safety Deliverables – Definition Stage
Update risk management plan
Facility Layout and Building Siting study
Consequence/Dispersion/Fire and Explosion Hazard analyses
FEED PHA
Preliminary SIL assignment and verification
FEED Safety Relief review and verification
Design and preliminary construction risk assessments

## Slide 9: Process Safety Deliverables – Execution Stage
Finalize risk management plan
EPC PHA
Final SIL assignment and verification
Evacuation, Escape, and Rescue validation
EPC Relief, Flare, and Blow Down System Design report and verification
Update Facility Layout and Building Siting study
Model Reviews (30/60/90)
Pre-Startup Safety Reviews (PSSR)
Formal handover of Risk Assessments/Register and Process Safety Studies to Operations

## Slide 10: Questions?