## Sheet1
Week | Dates | Course Events | Team Activities | Sam E. Conductor (Electrical) | Angie Near (Software) | Ray D. O'Signal (Systems/Software 2) | Saul Duringiron (Mechanical/Hardware 2)
1 | Jan. 13 - Jan. 19 | 0: Initial Project Proposal | Homework 0: Initial Project Proposal
2 | Jan. 20 - Jan. 26 | 1: Final Project Proposal, Project Schedule | 1: Final Project Proposal, Project Schedule
3 | Jan. 27 - Feb. 2 | 2: PCB Tutorial Exercise |  | 2: PCB Tutorial Exercise | 2: PCB Tutorial Exercise | 2: PCB Tutorial Exercise | 2: PCB Tutorial Exercise
4 | Feb. 3 - Feb. 9 | 3: Design Constraint Analysis, Prototyping Hardware Ordering and Acquisition |  |  |  | 3: Design Constraint Analysis
5 | Feb. 10 - Feb. 16 | 4: Packaging Design, Notebook Evaluation 1, Electrical Components Ordering |  |  |  |  | 4: Packaging Design
6 | Feb. 17 - Feb. 23 | Homework 5: Preliminary Schematic and Narrative |  |  |  | 5: Preliminary Schematic and Narrative
7 | Feb. 24 - Mar. 2 | Homework 6: Preliminary PCB Layout and Narrative |  | 6: Preliminary PCB Layout and Narrative
8 | Mar. 3 - Mar. 9 | Midterm Design Reviews, Peer Evaluation 1
9 | Mar. 10 - Mar. 16 | PCB Verification and Ordering | PCB Verification and Ordering
10 | Mar. 17 - Mar. 23 | Spring vacation, no classes
11 | Mar. 24 - Mar. 30 | Homework 9: Software Design Narrative |  |  | 9: Software Design Narrative
12 | Mar. 31 - Apr. 5 | 10: Patent Liability Analysis, Notebook Evaluation 2 |  | 10: Patent Liability Analysis
13 | Apr. 6 - Apr. 12 | 11: Reliability and Safety Analysis |  |  |  | 11: Reliability and Safety Analysis
14 | Apr. 13 - Apr. 19 | 12: Ethical and Environmental |  |  |  |  | 12: Ethical/Environmental Analysis
15 | Apr. 20 - Apr. 26 | Poster, User Manual | Poster, User Manual
16 | Apr. 27 - May. 2 | Final Report, Final Presentations, Senior Design Showcase, Notebook Evaluation 3, Peer Evaluation 2 | Final Report, Final Presentations, Senior Design Showcase, Notebook Evaluation 3, Peer Evaluation 2
17 | May. 3 - May. 9 | Finals Week