## Sheet1
Week | Dates | Course Events | Team Activities | Sam E. Conductor (Electrical) | Angie Near (Software) | Ray D. O'Signal (Systems/Software 2) | Saul Duringiron (Mechanical/Flex)
1 | Jan. 13 - Jan. 19 | 0: Initial Project Proposal (if not yet completed), 1: Final Project Proposal and Design Schedule | 0:Initial Project Proposal, 1:Final Project Proposal and Design Schedule, Team meetings established, Team photographs taken
2 | Jan. 20 - Jan. 26 | 2: Requirements Definition | 2: Requirements Definition
3 | Jan. 27 - Feb. 2 | 3: Functional Specification, 4: Electrical Overview, 5: Software Overview | 3: Functional Specification | 4: Electrical Overview | 5: Software Overview
4 | Feb. 3 - Feb. 9 | 6: Component Analysis, 7: Bill of Materials, Prototyping Hardware Acquisition and Ordering | 6: Component Analysis, 7: Bill of Materials, Prototyping Hardware Acquisition and Ordering |  | Development and third party software acquisition, Revision control configuration | Development and third party software acquisition, Revision control configuration
5 | Feb. 10 - Feb. 16 | 8: Mechanical Overview and CAD Design, 9: Software Formalization, Electrical Components Ordering | Electrical Components Ordering | PCB schematics/footprints/layout education | Development and third party software acquisition, Revision control configuration | 9: Software Formalization | 8: Mechanical Overview and CAD Design
6 | Feb. 17 - Feb. 23 | Preliminary Electrical Schematics, PCB Component Library |  | Preliminary Electrical Schematics, PCB Component Library | Microcontroller prototyping, Interface prototyping | Microcontroller prototyping, Interface prototyping | Assist electrical engineer
7 | Feb. 24 - Mar. 2 | Preliminary PCB Layout |  | Preliminary PCB Layout | Microcontroller prototyping, Interface prototyping | Microcontroller prototyping, Interface prototyping | Assist electrical engineer
8 | Mar. 3 - Mar. 9 | Midterm Design Review, Peer Evaluation 1 | Midterm Design Review Preparation, Peer Evaluation 1 | PCB and schematic efforts | Microcontroller prototyping, Interface prototyping | Microcontroller prototyping, Interface prototyping | Assist electrical engineer
9 | Mar. 10 - Mar. 16 | PCB Verification and Ordering |  | PCB Verification and Ordering | Functional development | Functional development | Assist electrical engineer
10 | Mar. 17 - Mar. 23 | Spring vacation, no classes
11 | Mar. 24 - Mar. 30 | 10: Legal Analysis, |  | PCB Assembly and hot air rework instruction | Functional development | Functional development | PCB Assembly and hot air rework instruction, 10: Legal Analysis
12 | Mar. 31 - Apr. 5 | 11: Reliability and Safety |  | Hardware verification, 11: Reliability and Safety | Functional development | Functional development | Hardware verification, Packaging assembly
13 | Apr. 6 - Apr. 12 | 12: Ethical and Environmental | System integration |  |  | 12: Ethical and Environmental
14 | Apr. 13 - Apr. 19 | 13: User Manual | System integration |  | 13: User Manual
15 | Apr. 20 - Apr. 26 | B1: Poster | System integration
16 | Apr. 27 - May. 2 | 14: ECE477 Educational Report, 15: Final Report, 16: Final Project Archive, Peer Evaluation 2, PSSC Demonstrations, Final Presentations, | 14: ECE477 Educational Report, 15: Final Report, 16: Final Project Archive, Peer Evaluation 2, PSSC Demonstrations, Final Presentations
17 | May. 3 - May. 9 | Finals Week