## Sheet1
Week | Dates | Course Events | Team Activities | Member 1 (Electrical) | Member 2 (Software) | Member 3 (Systems/Software 2) | Member 4 (Mechanical/Flex)
1 | Jan. 13 - Jan. 19 | 1: Final Project Proposal | 1:Final Project Proposal Team meetings established, Team photographs taken
2 | Jan. 20 - Jan. 26 | 2: Functional Specification | 2: Functional Specification
3 | Jan. 27 - Feb. 2 | 3: Electrical Overview, 4: Software Overview |  | 3: Electrical Overview | 4: Software Overview
4 | Feb. 3 - Feb. 9 | 5: Component Analysis, 6: Bill of Materials, Prototyping Hardware Acquisition and Ordering | 5: Component Analysis, 6: Bill of Materials, Prototyping Hardware Acquisition and Ordering |  | Development and third party software acquisition, Revision control configuration | Development and third party software acquisition, Revision control configuration
5 | Feb. 10 - Feb. 16 | 7: Mechanical Overview and CAD Design, Electrical Components Ordering | Electrical Components Ordering | PCB schematics/footprints/layout education | Development and third party software acquisition, Revision control configuration | Microcontroller prototyping, Interface prototyping | 7: Mechanical Overview and CAD Design
6 | Feb. 17 - Feb. 23 | Preliminary Electrical Schematics, PCB Component Library |  | Preliminary Electrical Schematics, PCB Component Library | Microcontroller prototyping, Interface prototyping | Microcontroller prototyping, Interface prototyping | Assist electrical engineer
7 | Feb. 24 - Mar. 2 | Preliminary PCB Layout, 8: Software Formalization |  | Preliminary PCB Layout | Microcontroller prototyping, Interface prototyping | 8: Software Formalization | Assist electrical engineer
8 | Mar. 3 - Mar. 9 | Midterm Design Review, Peer Evaluation 1 | Midterm Design Review, Peer Evaluation 1 | PCB and schematic efforts | Microcontroller prototyping, Interface prototyping | Microcontroller prototyping, Interface prototyping | Assist electrical engineer
9 | Mar. 10 - Mar. 16 | PCB Verification and Ordering |  | PCB Verification and Ordering | Functional development | Functional development | Assist electrical engineer
10 | Mar. 17 - Mar. 23 | Spring vacation, no classes
11 | Mar. 24 - Mar. 30 | 9: Legal Analysis, |  | PCB Assembly and hot air rework instruction | Functional development | Functional development | PCB Assembly and hot air rework instruction, 9: Legal Analysis
12 | Mar. 31 - Apr. 5 | 10: Reliability and Safety |  | Hardware verification, 10: Reliability and Safety | Functional development | Functional development | Hardware verification, Packaging assembly
13 | Apr. 6 - Apr. 12 | 11: Ethical and Environmental | System integration |  |  | 11: Ethical and Environmental
14 | Apr. 13 - Apr. 19 | 12: User Manual | System integration |  | 12: User Manual
15 | Apr. 20 - Apr. 26 | P2: Poster | System integration
16 | Apr. 27 - May. 2 | 13: ECE477 Educational Report, 14: Final Report, Peer Evaluation 2, PSSC Demonstrations, Final Presentations, | 13: ECE477 Educational Report, 14: Final Report, Peer Evaluation 2, PSSC Demonstrations, Final Presentations,
17 | May. 3 - May. 9 | Finals Week